## sprints
Feature | Database - design | User - Website | Application - Map | Application - Map Marker | Application - Detect Beacons | Application - route lnstructions
Storyboard | Design a website that displays information about the application and menus for the different aspects | User can view website and allows organisations to login and update their information
Sprint 1 | Database selection and initial design | Organisations send in registeration request - used to create orginisation in database | Present landing screen to user
Sprint 2 | ERD of Database | Landing page and option to allow organisation to sign in | Read in the Organisations Code to download data to the application
Sprint 3 | Implementation of database in SQL | Organisation view their details and can upload their maps | To show the map after download of data and option to select where the user would like to go.
Sprint 4 | Hosted site - implementation of database onto site | Organisation can upload/update information for navigation to work |  | Marker to display where your current location is |  | Show list of stepts to get from where you are to where you are going
Sprint 5 |  |  |  | Potentially Track User location | Detect where you are by using bluetooth beacons
Sprint 6 |  |  |  |  | Detect where you are by using NFC
Sprint 7 |  |  |  |  | Detect where you are by using QR Codes
Sprint 8 |  |  |  |  | Detect where you are by using Bar Codes
Sprint 9
Sprint 10
Sprint 11
Sprint 12
Sprint 13
Sprint 14
Sprint 15

## FBS
Purple for Finished: Yellow for Unfinished: | User - Website |  |  | Hours | Assigned to | Database - Design | Hours | Assigned to | Application - Map | Hours | Assigned to | Application - Map Marker | Hours | Assigned to | Application - Detect Beacons | Hours | Assigned to | Application - Route lnstructions | Hours | Assigned to
| User can view website and allows organisations to login and update their information |  |  |  | Kate | Design Database to handle website data and application data |  | Kevin | The map will display a 2d version of the building |  |  | The map will display a icon that the user will click or a dropdown-menu where all locations on the map are listed |  |  | User will be constantly detected using bluetooth beacon or will only be detected when reached a milestone |  |  | the user will be shown a path using a real time icon or a series of steps during each milestone
| Landing page and option to allow organisation to sign in |  |  |  | Kate | Database selection and initial design |  | Kate,Chris,Kevin | Present landing screen to user with information about the using the application |  | Chris | Display Icon on map or use drop down menu where all locations are listed |  | Kevin | Detect where you are by using bluetooth beacons |  | Chris | Display Path using shorted route algorithim |  | Chris
|  | Design and build landing page |  |  | Kate | ERD of Database |  | Kate,Chris,Kevin | Read in the Organisations Code to download data to the application |  | Kevin | Marker to display where your current location is |  | Chris | Detect where you are by using NFC |  | Kate | keep track of the users current progress on path |  | Kate
|  | User login and verify |  |  | Kevin | Implementation of database in SQL |  | Kevin | To show the map after download of data and option to select where the user would like to go. |  | Chris,Kate | Potentially Track User location |  | Kate | Detect where you are by using QR Codes |  | Kevin | Send user new instructions when milestone reached |  | Kevin
|  |  | user login screen |  | Kate | Hosted site - implementation of database onto site |  | Kevin | [6 empty] | Detect where you are by using Bar Codes |  | Kevin | Notify user when destination reached |  | Kevin
|  |  | user database |  | Kevin | Connectivity testing (web site / app) | [8 empty] | when user has reached a destination the nfc tag will send information to the user |  | Kate
|  | Organisation view their details and can upload their maps |  |  | Chris
|  | Organisation can upload/update information for navigation to work |  |  | Chris